## Slide 1: SkyMap
Team Deathstar
(Team 3)
Emma Batchelor, Lindsey Harris,
Joseph Noyes, Zein Sleiman

## Slide 2: Project Overview
To calculate the position of stars, planets, and other space objects
Generate a map as a JPEG image of the sky
  Shows position of various space objects relative to user location
  Named stars and planets will have labels
  Constellations will be labeled and be drawn with lines connecting each star
Implemented in Java

## Slide 3: Project Schedule
Sprint 1
  Setting up tools
  Getting to know the project
  CSV Reader
  Software Development Plan
Sprint 2
  Math formulas to Java
  Data Parser
  Basic GUI implementation
Sprint 3
  JPEG Generator
  Drawing Functions
  Architectural Design
Sprint 4
  Demo Presentation
  Advanced GUI Implementation
Sprint 5
  Final Testing and Debugging
  Presentation Preparations

## Slide 4: List of Deliverables
Software Development Plan - January 27, 2016
First Version of Backlog - February 15, 2016
Architecture Design and Updated Backlog - March 2, 2016
Presentation of Preliminary GUI - March 28, 2016
Product Delivery - April 20, 2016

## Slide 5: Personnel
Everyone is assigned the role of Developer. The Developer role encompasess the following tasks:
  Customer Liaison
  Designer
  Programmer
  Analyst
  Software Lead
  Software Tester
Zein: TrelloMaster, Joseph: GITMaster, Emma: GUI Expert, Lindsey: Lead Editor
The meeting moderator and recorder roles will be rotated
Scrum Master and Product Owner roles will also be rotated

## Slide 6: Risk Management Plan
Astronomical Mathematics
Drawing Functions
Excessive Ambition
Cross-platform Difficulties
Lack of Instructor Approval
Scheduling Conflicts
Weather Conflicts
Team Member Leaving
Losing Tools
Apocalypse

## Slide 7: Milestones
Documents:
  Software Dev Plan
  Requirements Definition Doc
  Software Design Doc
  Software Test Plan
Presentations:
  Presentation of Software Dev Plan (1/27)
  Presentation of first version of Backlog (2/15)
  Presentation of Architectural Design and updates to Backlog (3/2)
  Presentation of Preliminary GUI Design (3/28)
  Presentation of Final Product Delivery (4/18)

## Slide 8: Milestones cont’d
Software:
  Setting up dev tools: Trello, GIT, Google Calendar, IDEs
  Learning Java
  Preliminary GUI
  Writing astronomy formulas into Java
  JPEG Generator
  Drawing functions
  Final version of GUI

## Slide 9: Any Questions?
Questions you have, answer them we will.